## Roadmap
Refer also to this link for possible inputs: https://boeproject.atlassian.net/wiki/spaces/BP/pages/688143/Project+Roles
Phase | Description | Key Milestones | Start Date | End Date
Brainstorming and Problem Definition | Conduct team brainstorming sessions, define project scope, and refine the problem statement. | Project scope finalised, team charter signed. | 2025-01-29 | 2025-02-04
Research | Search relevant information and data to support hypothesis and the work | Exploratory work
Data Exploration and Methodology Design | Explore data sources, clean data, perform EDA, establish performance metrics for modeling, summary groups for testing (i.e. by topic, by speaker...) and targets | Data cleaned and methodologies designed. | 2025-02-05 | 2025-02-18
Modeling | Design NLP methodologies such as FinBERT, BERTopic, GenAI, Test models and run models evaluation
QA and insights checks | Monitor coding and also make sure that insights extracted from the data are in line with core objective
Benchmark analysis | Define innovative ways to analyse and compare data, such as benchmarking a firm against its peers
Pipeline development
Preliminary Solution Pitch | Prepare initial insights, develop a visual presentation, and submit a recorded pitch to stakeholders. | Recorded pitch submitted to stakeholders. | 2025-02-19 | 2025-02-25
Detailed Analysis and Reporting | Perform detailed data analysis, generate insights, work on final recommendations, draft the final report and presentation flow, and incorporate stakeholder feedback. | Final report drafted and reviewed. | 2025-02-26 | 2025-03-09
Final Presentation and Stakeholder Feedback | Present findings in a live session, deliver the final report, and gather feedback for project reflection. | Live presentation delivered, report submitted. | 2025-03-10 | 2025-03-17